## Version History
Date | Version | Desciption | Author
2026-02-02 | 4.1.0.3 | First Draft

## Test Scenario
Project Name | OpenCart (Frontend)
Reference Document | Functional Requirement Specification
Created By
Creation Date
Approval Date
Test Scenario ID | Reference | Test Scenario Description | Priority | Number of Test Cases
TS_001 | FRS | Validate the working of Register Account functionality | P0 | 7
TS_002 | FRS | Validate Login Functionality | P0 | 7
TS_003 | FRS | Validate Product Search Functionality | P1 | 6
TS_004 | FRS | Validate Add to Cart Functionality | P0 | 6
TS_005 | FRS | Validate Checkout Functionality | P0 | 8
TS_006 | FRS | Validate Logout Functionality | P1 | 3

## Register Account
Test Case ID | Test Scenario | Test Case Title | Pre-conditions | Test Steps | Test Data | Expected Result | Actual Result | Priority | Result | Remarks
TC_RA_001 | TS_001 | Verify Registeration with only mandatory fields | Open the Application in any browser and user on registration page | 1. Click on "My Account" Drop menu 2. click on Register option 3.Enter accounts details into field( First name , Last name, email, password & privacy poilcy) 4. Click on continue button (1st exepected result) 5. Click on continue (2nd Expected Result) | NA | 1. User should be logged in and taken to "Account successfully created " page. 2.User should be sent to "Account Page" and confirmation email should be sent to registration email. | 1. User has been successfully created 2. User was taken to "My account " page and received confirmation mail | P1 | Pass
TC_RA_002 | TS_001 | Verify error when mandatory fields are empty | Open the Application in any browser and user on registration page | 1. Click on "My Account" Drop menu 2. click on Register option 3.Leave all mandatory fields( first anme, last name, email, password) 4. Unchecked privacy policy box 5. Click on continue button | All fields = Blank | 1. Error messqage should be shown for each mandatory fields 2. Account should not be created 3. User should remain on registration page 4. Warning message should be shown for privacy policy checkbox | System displayed Username is already registered | P0 | Fail | BUG_001
TC_RA_003 | TS_001 | Verify invalid email format validation | Open the Application in any browser and user on registration page | 1. Click on "My Account" Drop menu 2. click on Register option 3. Fill all the fields( first name, last name, password, Tick the privacy policy checkbox) 4. Enter inavalid email 5. click on continue | Email: 122gmail.com | 1. Error: Invalid Email should be displayed 2. System should not allow registration | 1. System display Error: Email address does not appear to be valid 2. User is not created | P1 | Pass
TC_RA_004 | TS_001 | Verify Registration with existing Email | Open the Application in any browser and user on registration page | 1. Click on "My Account" Drop menu 2. Click on Register option and fill all the fields 3. Enter Email that is already existing in the system and accept privacy policy. 4. Click Continue | Email: vinaykuthey@gmail.com | System should display warning meesage like: email is already existing | System displayed Error: Email address is already registered! | P1 | Pass
TC_RA_005 | TS_001 | Verify confirmation email is sent after registration | Account registration is completed successfully | 1. Complete registration process 2. Open registered email inbox 3. Check for confirmation Email | Email: vinaykuthey@gmail.com | Confirmation email should be received in registered email inbox | Confirmation email was received on registered email | P2 | Pass
TC_RA_006 | TS_001 | Verify user redirected to the account page after registration | Registration Successful | 1. Complete valid registration 2. observe page after clicking on continue button | Valid registration datails | User should be redirected to the "My Account" page | User was successfully redirected to My Account page | P2 | Pass

## Login
Test Case ID | Test Scenario | Test Case Title | Pre-conditions | Test Steps | Test Data | Expected Result | Actual Result | Priority | Result | Remarks
TC_LI_001 | TS_002 | Verify Login with valid credentials | User account is already registered | 1. Click on "My Account" 2. Click on Login 3. Enter valid email & password 4. Click on Login button | email: vinaykuthey@gmail.com password: vin123# | User should be logged in successfully and redirected to the My Account page | User was succesfully Logged in and redirected to the my account page | P0 | Pass
TC_LI_002 | TS_002 | Verify Login with invalid password | User account is already registered | 1. Open login page 2. Enter valid email 3. Enter incorrect password 4. Click login | email: vinaykuthey@gmail.com password: wrong@123 | System should display warning message for invalid login | System display message "No match for Email and/or Password | P1 | Pass
TC_LI_003 | TS_002 | Verify login with unregistered email | login page is open | 1. Enter unregistered email 2. Enter password 3. Click Login | email: 1232gmail.com password: test@321 | System should display message like "Warning: email or password is incorrect | System display message "No match for Email and/or Password | P1 | Pass
TC_LI_004 | TS_002 | Verify login with empty fields | login page is open | 1. Leave email field blank 2. Leave password field blank 3. Click Login | email: blank Password: blank | User should remain on Login page | System display message "No match for Email and/or Password and User remains on login page | P0 | Pass
TC_LI_005 | TS_002 | Verify "Forgot Password" functionality | User account is already registered | 1. Click on Forgot password 2. Enter registered email 3. Click on continue | email: vinaykuthey@gmail.com | Password reset email should be sent to the registered email address | Password reset email was received by user on registered email | P2 | Pass
TC_LI_006 | TS_002 | Verify error message for invalid login | login page is open | 1. Enter Invalid email 2.Enter incorrect password 3. Click on login | email: 23#gmail.com password: hduwgqwuo | System should show warning meesage in red box | System show warning message "No match for email and /or Password" in red box | P1 | Pass
TC_LI_007 | TS_002 | Verify user is redirected to My Account page after login | User credentials are valid | 1. Enter valid login details 2.Click Login | email: vinaykuthey@gmail.com password: vin123# | User should be land on My Accound dashboard page | User was redirected to My account page | P1 | Pass

## Product Search
Test Case ID | Test Scenario | Test Case Title | Pre-conditions | Test Steps | Test Data | Expected Result | Actual Result | Priority | Result | Remarks
TC_PS_001 | TS_003 | Verify search with valid product name | User is on Home page | 1. Enter a valid product name in search box 2. Click search button | Product name: iPhone | System should display matching product in search results | System displays matching product "iPhone" in search results page | P0 | Pass
TC_PS_002 | TS_003 | Verify search with partial keyword | search bar is visible | 1. Enter partial keyword in search box 2. Click search | Keyword: Ipho | System should display products matching partial keyword | System displays matching product "iPhone" in search results page | P1 | Pass
TC_PS_003 | TS_003 | Verify search with invalid keyword | search bar is visible | 1. Enter invalid keyword 2. Click search | Keyword: xyz123 | System should display message like: There is no such product that matches search criteria | System display message: "There is no such product that matches search criteria" | P2 | Pass
TC_PS_004 | TS_003 | Verify search with empty input | search bar is visible | 1. Leave search box empty 2. Click search | Blank | System should either show all products or displays validation message | System display message: "There is no such product that matches search criteria" | P2 | Pass
TC_PS_005 | TS_003 | Verify search result displays correct products | Valid keyword id entered | 1. Enter valid keyword 2. Click search 3.Observe product list | Keyword: MacBook | Only relevant product related to the keyword should be displayed | System displays product "MacBook" in search results when searched with valid keyword | P1 | Pass
TC_PS_006 | TS_003 | Verify filter and sort options in search results | Search results page is displayed | 1. Perform search operation 2. Select different sort options( Price low to high, High to low) 3.Observe products order | Keyword: Samsung | Product should be sorted correctly based on selected options | Product are displayed in sorted order based on selected option | P2 | Pass

## Add to Cart
Test Case ID | Test Scenario | Test Case Title | Pre-conditions | Test Steps | Test Data | Expected Result | Actual Result | Priority | Result | Remarks
TC_AC_001 | TS_004 | Verify product can be added to cart | User is on product listing page | 1. Select any product 2. Click on add to cart button | Product: MacBook | Product should be added to the cart and success message should be displayed | System Displays "You have successfully added MacBook to your shopping cart" | P0 | Pass
TC_AC_002 | TS_004 | Verify product quantity update in cart | Product is already added | 1. Naviagte to the cart page 2. Change product quantity 3. Click update button | Quantity: 2 | Product quantity should be changed and total amount change accordingly | System displays Chnaged quantity and amount also changed accordingly | P1 | Pass
TC_AC_003 | TS_004 | Verify product removal from cart | Product exists in cart | 1. Go to cart page 2. Click remove product button | NA | Product should be romoved from cart and cart should be updated | System displays message: "You have removed an item from your shopping cart" and update cart | P1 | Pass
TC_AC_004 | TS_004 | Verify cart total calculation | Multiple products should be aaded to cart | 1. Add two or more products 2. Go to cart page 3. Verify subtotal and total amount | Product A: Rs.1000 Product B: Rs.1500 | Cart total should be equal to sum of product prices including taxes | Cart total calculated correctly including Eco tax and VAT | P1
TC_AC_005 | TS_004 | Verify cart persists after login | Product added as a guest user | 1. Add products to cart without login 2. Click login 3. Enter valid credentials 4. Navigate to cart | Valid user credentials | Cart items should remain in cart after login | Items are still there after login | P2 | Pass
TC_AC_006 | TS_004 | Verify cart icon updates after adding product | User is on product page | 1. Note current cart count 2. Add product to cart 3. Observe cart icon | Any product | Cart icon count should increase according to added quantity | Cart count is increased after changing quantity | P2 | Pass

## CheckOut
Test Case ID | Test Scenario | Test Case Title | Pre-conditions | Test Steps | Test Data | Expected Result | Actual Result | Priority | Result | Remarks
TC_CO_001 | TS_005 | Verify checkout with valid address | User logged in, product added to cart | 1. Open cart 2. Click checkout 3. Enter valid shipping adress 4. Select shipping method 5. Select payment method 6. Click confirm order | Name, City, Pin, Phone | Order should be placed successfully | Checkout cannot proceed because products in cart are marked as out of stock | P0 | Not executed
TC_CO_002 | TS_005 | Verify checkout without login | Product added to cart | 1. Add product to cart 2. Click Checkout 3. Observe system behaviour | NA | System should ask user to login before checkout | System show stock warning before checkout, so login verification can't be tested | P1 | Not executed
TC_CO_003 | TS_005 | Verify payment method selection | User on checkout page | 1. Proceed to checkout 2. View available methods 3. Select a payment option 4. Continue Checkout | Payment method: Cash on delivery, UPI | Selected payment method should be applied successfully | user can't reach payment method because checkout is blocked due to product stock issue. | P1 | Not executed
TC_CO_004 | TS_005 | Verify shipping method selection | User entered shipping address | 1. Go to checkout page 2. Enter shipping address 3. Select shipping method 4. Click continue | Shipping method: Flat rate | Selected shipping method should be applied to order | Shipping method page is not accessible because checkout can’t proceed due to stcok warning | P1 | Not executed
TC_CO_005 | TS_005 | Verify order confirmation page | Checkout process completed | 1. Complete checkout 2. Click confirm order | Valid order details | System should displaay order confirmation page with success message | Order confirmation pagre can't be reached because order can't be placed due to unavailability of product | P0 | Not executed
TC_CO_006 | TS_005 | Verify order ID generation | Order successfully placed | 1. Complete checkout process 2. Observe confirmation page | Valid checkout details | Unique order ID sghould be generate and displayed | Order ID can't be generate because order placement is not possible | P1 | Not executed
TC_CO_007 | TS_005 | Verify order appear in order history | User logged in and order placed | 1. Login to account 2. Go to my account 3. Click order history | NA | Newly placed order should be visible in order history | Order history can't be verified because order failed due to stock unavailability | P2 | Not executed
TC_CO_008 | TS_005 | Verify confirmation email after order placement | Order successfully placed | 1. Place an order 2. Open registered email inbox | Registered email adderess | Order confirmation email should be received | Confirmation email can't be verified since order was not placed | P2 | Not executed

## Logout
Test Case ID | Test Scenario | Test Case Title | Pre-conditions | Test Steps | Test Data | Expected Result | Actual Result | Priority | Result | Remarks
TC_LO_001 | TS_006 | Verify logout button functionality | User is logged into the application | 1. Login with valid credentials 2. Click on My account 3. Click Logout | Valid user credentials | User should be Logged out successfully | User got Logged out successfully after clicking logout | P0 | Pass
TC_LO_002 | TS_006 | Verify user session ends after logout | User logged in and session active | 1. Login to account 2. Click Logout 3. Try refresh tha page or perform any logged in action | Valid user credentials | User session should end and system should require login again | User session ended after logout and again login required | P0 | pass
TC_LO_003 | TS_006 | Verify user cannot access account page after logout | User logged in previously | 1. Login account 2. Click logout 3. enter URL on browser or press back button | Valid user credentials | System should redirect user to login page | User was able to accessaccount page using browser back button after logout | P0 | Fail | BUG_002

## RTM
Project Name | Open Cart |  |  | Project Name | Open Cart
Reference Doc |  |  |  | Refrence Doc
Created By |  |  |  | Created By
Created Date |  |  |  | Created Data
|  |  |  | Requirement ID | Test Scenarios | Description | Test CasesID
Requirement ID | Test Scenarios ID | Test Scenario Description | Test Cases ID | 1.1 | TS_001 | Validate the working of Register Account functionality | TC_RA_001
1.1 | TS_001 | Validate the working of Register Account functionality | TC_RA_001 |  |  |  | TC_RA_002
|  |  | TC_RA_002 |  |  |  | TC_RA_003
|  |  | TC_RA_003 |  |  |  | TC_RA_004
|  |  | TC_RA_004 |  |  |  | TC_RA_005
|  |  | TC_RA_005 |  |  |  | TC_RA_006
|  |  | TC_RA_006 | 1.2 | TS_002 | Validate Login Functionality | TC_LI_001
1.2 | TS_002 | Validate Login Functionality | TC_LI_001 |  |  |  | TC_LI_002
|  |  | TC_LI_002 |  |  |  | TC_LI_003
|  |  | TC_LI_003 |  |  |  | TC_LI_004
|  |  | TC_LI_004 |  |  |  | TC_LI_005
|  |  | TC_LI_005 |  |  |  | TC_LI_006
|  |  | TC_LI_006 |  |  |  | TC_LI_007
|  |  | TC_LI_007 | 1.3 | TS_003 | Validate Product Search Functionality | TC_PS_001
1.3 | TS_003 | Validate Product Search Functionality | TC_PS_001 |  |  |  | TC_PS_002
|  |  | TC_PS_002 |  |  |  | TC_PS_003
|  |  | TC_PS_003 |  |  |  | TC_PS_004
|  |  | TC_PS_004 |  |  |  | TC_PS_005
|  |  | TC_PS_005 |  |  |  | TC_PS_006
|  |  | TC_PS_006 | 1.4 | TS_004 | Validate Add to Cart Functionality | TC_AC_001
1.4 | TS_004 | Validate Add to Cart Functionality | TC_AC_001 |  |  |  | TC_AC_002
|  |  | TC_AC_002 |  |  |  | TC_AC_003
|  |  | TC_AC_003 |  |  |  | TC_AC_004
|  |  | TC_AC_004 |  |  |  | TC_AC_005
|  |  | TC_AC_005 |  |  |  | TC_AC_006
|  |  | TC_AC_006 | 1.5 | TS_005 | Validate Checkout Functionality | TC_CO_001
1.5 | TS_005 | Validate Checkout Functionality | TC_CO_001 |  |  |  | TC_CO_002
|  |  | TC_CO_002 |  |  |  | TC_CO_003
|  |  | TC_CO_003 |  |  |  | TC_CO_004
|  |  | TC_CO_004 |  |  |  | TC_CO_005
|  |  | TC_CO_005 |  |  |  | TC_CO_006
|  |  | TC_CO_006 |  |  |  | TC_CO_007
|  |  | TC_CO_007 |  |  |  | TC_CO_008
|  |  | TC_CO_008 | 1.6 | TS_006 | Validate Logout Functionality | TC_LO_001
1.6 | TS_006 | Validate Logout Functionality | TC_LO_001 |  |  |  | TC_LO_002
|  |  | TC_LO_002 |  |  |  | TC_LO_003
TC_LO_003

## Bug Report
Bug ID | Description | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | ScreenShot
BUG_001 | Incorrect error message displayed when mandatory fields are left blank during registration | 1. Click on "My Account" Drop menu 2. click on Register option 3.Leave all mandatory fields( first anme, last name, email, password) 4. Unchecked privacy policy box 5. Click on continue button | System should display validation messages for mandatory fields only | System displays message "Username is already registered!" even when username is blank | Medium | P0
BUG_002 | User can access account page after logout using browser back button | 1. Login with valid credentials 2. click on My account 3. cliclk logout 4. Press browser back button 5. Observe account login | System should redirect user to login page after logout and do not allow access to account page | user is able to access account page using browser back button even after logout | Medium | P0
BUG_003 | Search allows special characters and shows irrelevant results instead of validation message | 1. Open OpenCart home page 2. Go to search bar 3. Enter special characters like @@##* 4. Click search | System should display validation message for inavalid keyword | System performs search and shows results or empty page instead of validation message | Low | P2
BUG_004 | Checkout Button visible even when product is out of stock | 1. Add product to cart 2. Product shows (out of stock warning) 3. Go to cart page 4. Observe checkout button | Checkout button should be disabled or hidden when product is out of stock | Checkout button is still visible even when product is out of stock | Medium | P1